## Sheet1
Product : APP KUBE |  | Date: 08-feb-2024
Module : POLICY
Test policy By : Syed Annas Ahmed
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_001 | Character Limit Issue in Policy Creation Search for Users | When search a policy, the search function for users does not impose a character limit, leading to potential issues. | While creating a new policy, the search feature for selecting users to include in the policy does not enforce a character limit. As a result, users can input a large number of characters without any restrictions. This behavior may lead to performance issues or unexpected behavior, especially when dealing with a large number of users. | Log in to the Application Navigate to the policy creation section. Use the search functionality to find users to include in the policy. Input a large number of characters in the search field. Observe that the search field accepts the input without any restrictions. | Medium | High | Open | APP KUBE | https://ibb.co/9GRpzZG | This issue can potentially impact Application performance and user experience, particularly in environments with a large user base. It is recommended to implement a character limit restriction to prevent abuse and ensure optimal Application operation. | Syed Annas Ahmed
Def_002 | All Access Selected for Deletion in Role Based Access Control | All Access are selected for deletion in Role Based Access Control (RBAC) even when not intended by the user. | When navigating to the Role Based Access Control (RBAC) section within the AppKube dashboard and accessing the policies, All Access are automatically selected for deletion. This behavior occurs without user input and may lead to unintended deletion of important policies. | Log in to the AppKube application. Navigate to the dashboard. Click on the settings icon. Select Role Based Access Control (RBAC). Click on the 'Users and Policies' button. Navigate to the policies section. Observe that All Accessare pre-selected for deletion. | Medium | High | Open | AppKube | https://ibb.co/7vDjVRx | The automatic selection of All Access for deletion poses a risk of inadvertent data loss or disruption to system functionality. It is crucial to address this issue promptly to prevent accidental deletion of critical policies. | Syed Annas Ahmed
Def_003 | No Character Limit in Policy Name and Description Fields | The policy name and description fields do not enforce character limits during policy creation. | When creating a new policy in the AppKube application, the fields for policy name and description allow users to input an unlimited number of characters. This lack of character limit can lead to unintended behavior, such as performance issues, data corruption, or display errors. | Log in to the AppKube application. Navigate to the policy creation page. Click on the 'Create Policy' button. Observe that the policy name and description fields have no character limit. Attempt to input a large number of characters in both fields, including numbers. Verify that the input is accepted without any restrictions. | Medium | High | Open | AppKube | https://ibb.co/yQJg0qQ | The absence of character limits in the policy name and description fields may lead to usability issues and data inconsistencies. It is recommended to implement character limits to ensure data integrity and optimal user experience. | Syed Annas Ahmed
Def_004 | Unable to Delete Newly Created Policies | After creating a new policy, it cannot be deleted from the Application | When attempting to delete a policy that has been newly created, the Application does not allow deletion showing error. The delete action does not result in the policy being removed from the Application and it remains intact. | Log in to the Appkube Navigate to the policy section. Create a new policy. Attempt to delete policy. Observe that the policy remains undeleted despite attempting deletion. | High | High | Open | APP KUBE | https://ibb.co/qFk9sGk | Despite repeated attempts to delete newly created policies, the Applicationn fails to execute the delete action, indicating a critical flaw in the policy management functionality. This issue significantly impairs the Application usability and compliance capabilities, necessitating immediate investigation and resolution to ensure proper policy administration and data integrity. | Syed Annas Ahmed
Product : APP KUBE |  | Date: 12-feb-2024
Module : POLICY
Test policy By : Syed Annas Ahmed
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_005 | Missing Error Message for Description Field Limit Exceeded | When creating a new policy in the App Kube Application, the Description field lacks proper validation for character limits. Users are not shown an error message when they exceed the character limit for the Description field, leading to potential data inconsistency and confusion. | During the creation of a new policy in the App Kube Application, users are required to input a policy name and description. However, there is no validation in place to restrict the number of characters entered in the Description field. Consequently, when users exceed the allowed character limit for the Description, no error message is displayed to notify them of the issue. This results in users being able to create policies with descriptions that are longer than intended, potentially leading to data integrity issues. | 1. Log in to the Kube Application. 2. Navigate to Settings > Users and Permissions > Policies. 3. Click on "Create New Policy". 4. Enter a Policy Name. 5. Enter a lengthy description exceeding the character limit (e.g., 500 characters). 6. Click on "Create Policy". 7. Observe that the application allows the policy creation without displaying any error message related to the Description field character limit. | Medium | High | Open | APP KUBE | https://ibb.co/gWkWCpz | This issue affects user experience and data integrity by allowing policies with descriptions exceeding the character limit to be created without proper validation. | Syed Annas Ahmed
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def__006 | Incorrect Case in Displayed Policy Name and Description | Navigate to the Create policy from the user ansd permission section, the system displays the policy name and policy description with the first letter in lowercase instead of the expected uppercase. | Upon accessing the "Create Policy" page from the "User and Permission" section, it is observed that the policy name and policy description display the first letter in lowercase, contrary to the expected behavior. The convention for proper nouns and titles should have the first letter capitalized | 1. Log in to the Kube Application. 2. Navigate to Settings > Users and Permissions > Policies. 3. Click on "Create New Policy". 4. Enter a Policy Name. 5. Enter a lengthy description exceeding the character limit (e.g., 500 characters). 6. Click on "Create Policy". | Low | Low | Open | AppKube | https://ibb.co/vvL6QDD | The display of the policy name and policy description with the first letter in lowercase is a deviation from the expected convention and can impact the overall user experience. Urgent attention is required to address this bug and ensure that the system displays the first letter in uppercase for both the policy name and description. | Syed Annas Ahmed

## Sheet2
Product : APP KUBE |  | Date: 12-feb-2024
Module : Role
Test By : mohd niyaz ullah
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_001 | Dropdown Box Not Closing After Selecting Policy in Role Creation | The dropdown box for selecting a policy does not close after selecting "All access" or "No access" when creating a new role in the AppKube application. | When creating a new role in the AppKube application and selecting a policy from the dropdown box, the dropdown box remains open even after the selection is made. This prevents users from easily moving to the next step in the role creation process, as the open dropdown box obstructs their view and interaction with other elements on the page. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. On the same page, click on the "Role Module" section. 8. Click on the "Create New Role" button. 9. In the role creation form, click on the dropdown box for selecting a policy. 10. Select either "All access" or "No access" from the dropdown options. 11. Observe that the dropdown box remains open even after making the selection. | Low | Medium | Open | AppKube | https://ibb.co/Dk84FMB | The issue with the dropdown box not closing after policy selection affects the user experience and workflow during role creation. Implementing a fix to automatically close the dropdown box upon policy selection will improve usability and streamline the role creation process. | mohd niyaz ullah
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_002 | Inability to Delete Selected Policy Sets | Users are unable to delete selected policy sets when prompted in the AppKube application. | When attempting to delete selected policy sets in the AppKube application, users encounter a problem where the deletion process fails to execute despite confirmation. After selecting the policy sets and clicking on the delete button, a confirmation prompt is displayed asking "Do you want to delete?" However, upon confirming the deletion by clicking "Delete," the action does not proceed, and the selected policy sets remain unchanged. This issue prevents users from effectively managing policy sets, potentially leading to clutter and confusion in the application's configuration. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Select the policy sets to be deleted. 8. Click on the delete button. 9. Confirm the deletion when prompted. 10. Observe that the selected policy sets are not deleted despite confirmation. | High | High | Open | AppKube | https://ibb.co/P61JLkL | The inability to delete selected policy sets impedes users' ability to manage access control effectively. A resolution is necessary to ensure proper functionality and usability of the application's policy management features. | mohd niyaz ullah
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_003 | Missing Alert Message for Exceeding Character Limit in Role Description Field | Users are not alerted when exceeding the character limit in the role description field during role creation in the AppKube application. | When creating a new role in the AppKube application and entering text into the "Role Description" field, there is a character limit imposed on the input. However, when the user exceeds this limit, there is no alert message or indication provided to notify them of the constraint. As a result, users may inadvertently exceed the character limit without realizing it, leading to truncated or incomplete role descriptions. This issue diminishes user experience and may result in confusion regarding the proper length of role descriptions. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the "Role Module" section. 8. Click on the "Create New Role" button. 9. Enter text into the "Role Description" field exceeding the character limit. 10. Observe that no alert message is displayed indicating the character limit has been exceeded. | Medium | Medium | Open | AppKube | https://ibb.co/tPzsFcX | The absence of an alert message for exceeding the character limit in the role description field hinders user awareness and may lead to unintended consequences such as truncated or incomplete role descriptions. Implementing an alert message will improve user experience and prevent confusion. | mohd niyaz ullah
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_004 | Incorrect Button Label "Edit" Instead of "Update" When Editing Role | The button label remains as "Edit" instead of changing to "Update" after modifying a role in the AppKube application. | When editing a role in the AppKube application and making changes to its settings or description, the button label for saving the changes remains as "Edit" instead of updating to "Update." This inconsistency in button labeling may cause confusion for users, as they may expect the button to reflect the action of updating the role with the changes made. Instead, the button label remains the same as when initially accessing the edit mode, potentially leading to user errors or misunderstandings regarding the purpose of the button. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the "Role Module" section. 8. Create a new role or select an existing role to edit. 9. Click on the three dots menu from the left side of the role. 10. Select "Edit Role" from the popup options. 11. Modify the role settings or description. 12. Observe that the button label remains as "Edit" instead of changing to "Update" to reflect the action of saving the changes. | Low | Medium | Open | AppKube | https://ibb.co/mXYXg8Q | The inconsistency in button labeling when editing a role may lead to user confusion or misunderstanding of the action performed. Updating the button label to "Update" will enhance clarity and usability of the application's interface. | mohd niyaz ullah

## Sheet3
Module : Incorrect Display of Active Status in Role based Access Control Permissions |  | Date: 08 feb 2024
Test Login By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_003 | Incorrect Display of Active Status in Role based Access Control Permissions | The active status of permissions in the Role based Access Control section is inaccurately displayed, showing all permissions as active regardless of the actual selection status. | Upon navigating to the Role based Access Control section in the admin page and selecting permissions for modules such as "Enviroment", "Product", "SRE", and "DevSecOps", the active status is consistently displayed as active for all permissions, irrespective of whether they are selected or not. This discrepancy misleads users into believing that all permissions are active, potentially leading to incorrect access management. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to "Role based Access Control." 7. Click on the permissions icon for modules such as "Enviroment", "Product", "SRE", and "DevSecOps". 8. Observe that the active status for permissions within each module appears as active, regardless of the actual selection status. 9. Verify that even after selecting or deselecting permissions, the active status remains unchanged. | Medium | High | Open | AppKube | https://ibb.co/c8BMsfK https://ibb.co/B2sRSTx https://ibb.co/GkqPr1s https://ibb.co/vq8M2wj https://ibb.co/WzsJf8w https://ibb.co/M96dGBM & https://ibb.co/FmShXty | This bug significantly affects the accuracy of access management within the application, potentially leading to security risks and mismanagement of permissions. It requires immediate attention to ensure the correct display of permission status in the Role based Access Control section. | Mohammed Sohail
Module : Newly Created User Data Not Visible After Successful Creation |  | Date: 08 feb 2024
Test Login By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_001 | Newly Created User Data Not Visible After Successful Creation | After successfully creating a user and deleting a user in the Role based Access Control section, newly created user data is not visible in the user information section. | Upon successfully creating a user in the Role based Access Control section following the deletion of another user, the newly created user's data fails to appear in the user information section below the create button. This issue persists despite successful creation, hindering administrators' ability to view and manage user data effectively. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to "Role based Access Control." 7. Click on the user icon. 8. Select the user and click on the 3 dots below the table information about the user to delete the user successfully. 9. After deletion, attempt to create a new user using the "Create" button on the same page. 10. Verify that the user creation process completes successfully. 11. Check the user information section below the create button for visibility of the newly created user's data. | Medium | High | Open | AppKube | https://ibb.co/xh11Cbc | This bug impacts the usability of the application, particularly in managing user permissions. It requires immediate attention to ensure smooth user management processes. | Mohammed Sohail
Module : Edit Option Not Functional in Role based Access Control |  | Date: 08 feb 2024
Test Login By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_002 | Edit Option Not Functional in Role based Access Control | The "Edit" option in the Role based Access Control section is not functional despite being selected by the user. | Upon navigating to the Role based Access Control section in the admin page and selecting the "Edit" option for a user account, the functionality fails to execute. Despite the user selecting the "Edit" option from the pop-up menu that appears upon clicking the three dots below the table information about the user, no action is performed, preventing users from modifying user account details as intended. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to "Role based Access Control." 7. Click on the user icon. 8. Select the user and click on the three dots below the table information about the user account. 9. From the pop-up menu, select the "Edit" option. 10. Observe that the edit functionality does not execute or display any action. | High | High | Open | AppKube | https://ibb.co/6ncknyz | This bug significantly impacts the user's ability to manage user accounts effectively within the application. Immediate attention is required to restore the functionality of the edit option in the Role based Access Control section. | Mohammed Sohail
Module : Reset Password Functionality Skips Current Password Verification |  | Date: 12 feb 2024
Test Login By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_003 | Reset Password Functionality Skips Current Password Verification | The reset password functionality skips the step of verifying the current password, posing a security risk. | When attempting to reset a user's password in the AppKube application, the reset password functionality skips the step of verifying the current password. Instead, it directly prompts the user to enter a new password and confirm it, without requiring the current password for authentication. This behavior poses a security risk as it allows an unauthorized user who gains access to the account to change the password without having to provide the current password, thereby bypassing authentication measures. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the User icon on the same page. 8. On the User module, click on the user's name to navigate to their profile. 9. Click on the "Security Credentials" module. 10. Click on the "Reset Password" option. 11. Observe that the reset password form does not prompt for the current password. | Medium | High | Open | AppKube | https://ibb.co/yddkm2y | It is recommended to implement proper authentication measures, such as requiring the current password before allowing a password reset, to mitigate this security risk. | Mohammed Sohail
Module : Missing Logout Alert After Password Change |  | Date: 12 feb 2024
Test Login By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_004 | Missing Logout Alert After Password Change | The application does not provide an alert message prompting the user to log out after changing the password. | After changing the password in the AppKube application, there is no alert message displayed to the user asking if they want to log out manually or informing them that they will be logged out automatically. This absence of notification can lead to confusion for users who are unaware that a password change typically requires a reauthentication process. As a result, users may unintentionally remain logged in with outdated credentials, posing a security risk. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the User icon on the same page. 8. On the User module, click on the user's name to navigate to their profile. 9. Click on the "Security Credentials" module. 10. Click on the "Reset Password" option. 11. Enter a new password and confirm it. 12. Observe that there is no alert message indicating the need to log out. | Low | Medium | Open | AppKube | https://ibb.co/j8vK3NG | Implementing an alert message after password change is essential for user awareness and security purposes, ensuring that users are prompted to log out and reauthenticate with their new credentials. | Mohammed Sohail
Module : Unresponsive "Remove" Button in User Profile Groups Section |  | Date: 12 feb 2024
Test Login By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_005 | Unresponsive "Remove" Button in User Profile Groups Section | The "Remove" button in the User Profile Groups section becomes unresponsive after selecting a group name. | Upon navigating to a user's profile in the AppKube application and selecting a group name in the Groups section, the "Remove" button fails to respond when clicked. This prevents users from removing themselves or others from groups, hindering the functionality of group management within the application. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the User icon on the same page. 8. On the User module, click on the user's name to navigate to their profile. 9. Click on the Group on the same page and select a group name. 10. Observe that the "Remove" button is displayed. 11. Click on the "Remove" button. 12. Observe that the button does not respond. | Medium | High | Open | AppKube | https://ibb.co/vjC6FNx | This issue significantly impacts the usability of the application, particularly in managing user groups. A fix is necessary to ensure smooth group management functionality. | Mohammed Sohail
Module : Error Message "User Deletion failed!" When Disabling User |  | Date: 12 feb 2024
Test Login By : Mohammed Sohail
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
DID_006 | Error Message "User Deletion failed!" When Disabling User | An error message "User Deletion failed!" is displayed when attempting to disable a user in the user profile settings. | When attempting to disable a user in the AppKube application by clicking on the Disable User button in the user profile settings, an error message "User Deletion failed!" is displayed instead of a confirmation message or the user being successfully disabled. This error message does not accurately reflect the action being performed, as disabling a user should not result in a deletion operation. Additionally, it fails to provide any specific information or guidance regarding the cause of the failure, making it challenging for users to understand and address the issue. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the User icon on the same page. 8. On the User module, click on the user's name to navigate to their profile. 9. Click on the "Disable User" button. 10. Confirm the action when prompted. 11. Observe the error message "User Deletion failed!" | High | High | Open | AppKube | https://ibb.co/vjC6FNx | The error message is misleading and lacks specificity, causing confusion for users attempting to disable a user account. A more accurate and informative error message should be displayed to help users understand and resolve the issue effectively. [Your | Mohammed Sohail

## Sheet4
MODULE : | GROUP
TESTED BY : | mohd niyaz ullah | Date:12-feb-2024
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def__001 | Lack of Alert for Unlimited Group Description Input | The application fails to display an alert message when entering an unlimited number of words in the Group Description field while adding a user in the Super Admins page. | The system does not provide any warning or alert when a user exceeds the expected word limit for the Group Description in the Super Admins page. The absence of this alert may lead to user confusion, as there is no indication of the allowed word limit for the Group Description. | Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission. Navigate to the Group section Select the "Group" option Click on "Create new group." In the user addition form, enter an extensive amount of text in the "Group Description" field. Observe that there is no alert message indicating the exceeded word | High | Medium | Open | Appkube | https://ibb.co/vvyZN6Q | The application should provide a clear alert message when users exceed the word limit in the Group Description field. Consider adding information about the allowed word limit for Group Description to improve user guidance and experience. | Tester
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def__002 | : Remove Button Not Functional in Super Admins Page | When navigating to the Super Admins page from the "View Group" section and attempting to remove a user using the "Remove" button, the action is not working as expected | Upon accessing the Super Admins page from the "View Group" section, the "Remove" button does not perform the expected action of removing the selected user. The user remains in the Super Admins list even after clicking the "Remove" button. | Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission Select the "Group" option. Click on "Create new group." Navigate to "user and permission page" section. select created group Attempt to remove the user by clicking on the "Remove" button. | High | High | Open | Appkube | https://ibb.co/J30wBLv | The inability to remove users from the Super Admins list is a critical issue, as it affects the application's user management functionality. Urgent attention is required to address this bug and ensure proper functionality of the "Remove" button | Tester
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def__003 | Edit Button Not Functional in Super Admins Page | When navigating to the Super Admins page from the "View Group" section and attempting to edit a user using the "Edit" button, the action is not working as expected. | Upon accessing the Super Admins page from the "View Group" section, the "Edit" button does not perform the expected action of allowing the modification of user details. Clicking on the "Edit" button does not open the necessary form or dialog to edit the user's information. | Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission. Select the "Group" option Click on "Create new group." Navigate to the user and permission page Add a user to the view group list. Attempt to edit the user details by clicking on the "Edit" button. | High | High | Open | AppKube | https://ibb.co/nw27VSC | The inability to edit user details using the "Edit" button in the Super Admins page is a critical issue, affecting the application's user management functionality. Urgent attention is required to address this bug and ensure proper functionality of the "Edit" button
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def__004 | Disallowed Permission Option Available Without Data | When navigating to the Super Admins page from the "View Group" section and attempting to manage disallowed permissions for a user, the option is available, but no data is displayed, making it impossible to select or modify disallowed permissions. | Upon accessing the Super Admins page from the "View Group" section and adding a user, the option to manage disallowed permissions is visible. However, upon attempting to interact with the disallowed permissions, no data is presented, preventing users from selecting or modifying any disallowed permissions. | Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission. Select the "Group" option Click on "Create new group." Navigate to the user and permission from the "Group" section Add a user to the new created grfoup. Attempt to manage disallowed permissions for the added user | Critical | High | Open | AppKube | https://ibb.co/DQ7LvGr | The presence of the disallowed permission option without displaying any data is a critical issue, as it prevents administrators from managing user permissions effectively. Urgent attention is required to address this bug and ensure that disallowed permissions can be properly configured. | Tester
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def__005 | Incorrect Popup Message on Deleting User-Created Group | The system displays an inaccurate pop-up message when attempting to delete a user-created group on the Overview Group page. | When a user-created group is selected, and the admin clicks on the "Delete" button on the Overview Group page, the system incorrectly informs the admin that the group cannot be deleted. However, the system should allow the deletion of user-created groups | Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission. Select the "Group" option Click on "Create new group." Navigate to the "user and permission page" Select a user-created group. Observe the pop-up message incorrectly stating that the group cannot be deleted Click on the "Delete" button. | High | High | Open | AppKube | https://ibb.co/Mh6ybCh | The system should allow the deletion of user-created groups, and the pop-up message should accurately reflect the possibility of deleting the selected group. Review the logic behind the "Delete" operation for user-created groups to ensure proper functionality. | Tester
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def__006 | Role Not Added Successfully in Overview Page | When navigating to the "User and Permission" page from the "View Group" section, adding a user, selecting a role, and clicking on "Add Role" appears to be successful. However, the role is not added to the overview page as expected. | Upon accessing the "User and Permission" page from the "View Group" section and adding a user, selecting a role, and adding the role, the process completes without errors. However, upon navigating to the overview page, the added role is not displayed, indicating a failure in adding the role to the system | Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission Select the "Group" option. Click on "Create new group." Navigate to "user and permission page" section. select created group Attempt to remove the Select a role and click on "Add Role Navigate to the overview page and observe that the added role is not displayed. | High | High | open | AppKube | https://ibb.co/pXjKscB | The failure of the added role to appear in the overview page impacts the application's functionality and user expectations. Urgent attention is required to investigate and address this bug to ensure that roles are properly added and reflected in the system. | Tester

## Sheet5
Product : APP KUBE |  | Date: 09-feb-2024
Module :Two-Factor Authentication
Test By : Syed Annas Ahmed
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_001 | Two-Factor Authentication (2FA) OTP Validation Failure | The system fails to validate the OTP (One-Time Password) during the Two-Factor Authentication (2FA) setup process. | After following the steps to set up 2FA in the App Kube, including entering the username and password, scanning the QR code, and entering the received OTP, clicking the "Validate" button results in the system displaying an error message indicating that the OTP validation has failed. | login the App Kube . Navigate to the Settings section. Select "Two-Factor Authentication." Click on the option to enable 2FA. Enter the username and password when prompted. Click on the "Next" button. Scan the provided QR code with a compatible device. Receive the OTP. Enter the OTP in the designated field. Click on the "Validate" button. | High | Medium | Open | APP KUBE | https://ibb.co/Yfhr3CX | This issue prevents users from successfully completing the setup of 2FA, potentially leaving their accounts vulnerable to unauthorized access. | Syed Annas Ahmed
Def_002 | Lack of Username and Password Character Limit Validation and Error Messages for Numbers and Symbols. | The Application fails to enforce a character limit for usernames and passwords during the Two-Factor Authentication (2FA) setup process and does not display error messages when numbers and symbols are entered in the respective fields. | When attempting to set up 2FA in the App Kube, users can input usernames and passwords without encountering any character limit validation. Additionally, when entering numbers or symbols in the username or password field, the system does not prompt an error message to notify users about invalid characters. | Login to the App Kube. Navigate to the Settings section. Select "Two-Factor Authentication." Click on the option to enable 2FA. Enter a username with more characters than the allowed limit (if any) and/or containing numbers and/or symbols. Enter a password with more characters than the allowed limit (if any) and/or containing numbers and/or symbols. Continue with the 2FA setup process. | Medium | High | Open | APP KUBE | https://ibb.co/R9639dh | This issue compromises the integrity of the username and password input fields during 2FA setup, potentially leading to usability issues and security concerns. | Syed Annas Ahmed
Def_003 | Opening Blank Page Instead of Displaying Error Message When Alphabets Entered in OTP Field | The application opens a blank page instead of displaying an error message when alphabets are entered in the OTP (One-Time Password) field during the Two-Factor Authentication (2FA) setup process. | Upon scanning the QR code and proceeding to the OTP page during the 2FA setup process in the App Kube Application, if alphabets are entered in the designated OTP field, the application fails to validate the input and instead opens a blank page without providing any feedback or error message to the user. | Login to the App Kube Application. Navigate to the Settings section. Select "Two-Factor Authentication." Click on the option to enable 2FA. Scan the provided QR code. Proceed to the OTP page. Enter alphabets in the designated OTP field. Click on the "Next" button or attempt to proceed. | Medium | High | Open | APP KUBE | https://ibb.co/37m5wVv | This issue leads to confusion and a lack of feedback for users during the 2FA setup process, potentially causing frustration and hindering successful completion of the setup. | Syed Annas Ahmed
After enter Alphabets https://ibb.co/5c0rnrS