## Sheet1
Product : APP KUBE |  | Date: 11-Mar-2024
Module : POLICY
Test policy By : Syed Annas Ahmed
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_001 | Character Limit Issue in Policy Creation Search for Users | When search a policy, the search function for users does not impose a character limit, leading to potential issues. | While creating a new policy, the search feature for selecting users to include in the policy does not enforce a character limit. As a result, users can input a large number of characters without any restrictions. This behavior may lead to performance issues or unexpected behavior, especially when dealing with a large number of users. | Log in to the Application Navigate to the policy creation section. Use the search functionality to find users to include in the policy. Input a large number of characters in the search field. Observe that the search field accepts the input without any restrictions. | Medium | High | Open | APP KUBE | https://ibb.co/9GRpzZG | This issue can potentially impact Application performance and user experience, particularly in environments with a large user base. It is recommended to implement a character limit restriction to prevent abuse and ensure optimal Application operation. | Syed Annas Ahmed
Def_002 | All Access Selected for Deletion in Role Based Access Control | All Access are selected for deletion in Role Based Access Control (RBAC) even when not intended by the user. | When navigating to the Role Based Access Control (RBAC) section within the AppKube dashboard and accessing the policies, All Access are automatically selected for deletion. This behavior occurs without user input and may lead to unintended deletion of important policies. | Log in to the AppKube application. Navigate to the dashboard. Click on the settings icon. Select Role Based Access Control (RBAC). Click on the 'Users and Policies' button. Navigate to the policies section. Observe that All Accessare pre-selected for deletion. | Medium | High | Open | AppKube | https://ibb.co/7vDjVRx | The automatic selection of All Access for deletion poses a risk of inadvertent data loss or disruption to system functionality. It is crucial to address this issue promptly to prevent accidental deletion of critical policies. | Syed Annas Ahmed
Def_003 | No Character Limit in Policy Name and Description Fields | The policy name and description fields do not enforce character limits during policy creation. | When creating a new policy in the AppKube application, the fields for policy name and description allow users to input an unlimited number of characters. This lack of character limit can lead to unintended behavior, such as performance issues, data corruption, or display errors. | Log in to the AppKube application. Navigate to the policy creation page. Click on the 'Create Policy' button. Observe that the policy name and description fields have no character limit. Attempt to input a large number of characters in both fields, including numbers. Verify that the input is accepted without any restrictions. | Medium | High | Open | AppKube | https://ibb.co/yQJg0qQ | The absence of character limits in the policy name and description fields may lead to usability issues and data inconsistencies. It is recommended to implement character limits to ensure data integrity and optimal user experience. | Syed Annas Ahmed
Def_004 | Unable to Delete Newly Created Policies | After creating a new policy, it cannot be deleted from the Application | When attempting to delete a policy that has been newly created, the Application does not allow deletion showing error. The delete action does not result in the policy being removed from the Application and it remains intact. | Log in to the Appkube Navigate to the policy section. Create a new policy. Attempt to delete policy. Observe that the policy remains undeleted despite attempting deletion. | High | High | Open | APP KUBE | https://ibb.co/qFk9sGk | Despite repeated attempts to delete newly created policies, the Applicationn fails to execute the delete action, indicating a critical flaw in the policy management functionality. This issue significantly impairs the Application usability and compliance capabilities, necessitating immediate investigation and resolution to ensure proper policy administration and data integrity. | Syed Annas Ahmed
Product : APP KUBE |  | Date: 11-Mar-2024
Module : POLICY
Test policy By : Syed Annas Ahmed
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to | Assigned to
Def_005 | Missing Error Message for Description Field Limit Exceeded | When creating a new policy in the App Kube Application, the Description field lacks proper validation for character limits. Users are not shown an error message when they exceed the character limit for the Description field, leading to potential data inconsistency and confusion. | During the creation of a new policy in the App Kube Application, users are required to input a policy name and description. However, there is no validation in place to restrict the number of characters entered in the Description field. Consequently, when users exceed the allowed character limit for the Description, no error message is displayed to notify them of the issue. This results in users being able to create policies with descriptions that are longer than intended, potentially leading to data integrity issues. | 1. Log in to the Kube Application. 2. Navigate to Settings > Users and Permissions > Policies. 3. Click on "Create New Policy". 4. Enter a Policy Name. 5. Enter a lengthy description exceeding the character limit (e.g., 500 characters). 6. Click on "Create Policy". 7. Observe that the application allows the policy creation without displaying any error message related to the Description field character limit. | Medium | High | Open | APP KUBE | https://ibb.co/gWkWCpz | This issue affects user experience and data integrity by allowing policies with descriptions exceeding the character limit to be created without proper validation. | Syed Annas Ahmed
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to | Assigned to
Def__006 | Incorrect Case in Displayed Policy Name and Description | Navigate to the Create policy from the user ansd permission section, the system displays the policy name and policy description with the first letter in lowercase instead of the expected uppercase. | Upon accessing the "Create Policy" page from the "User and Permission" section, it is observed that the policy name and policy description display the first letter in lowercase, contrary to the expected behavior. The convention for proper nouns and titles should have the first letter capitalized | 1. Log in to the Kube Application. 2. Navigate to Settings > Users and Permissions > Policies. 3. Click on "Create New Policy". 4. Enter a Policy Name. 5. Enter a lengthy description exceeding the character limit (e.g., 500 characters). 6. Click on "Create Policy". | Low | Low | Open | AppKube | https://ibb.co/vvL6QDD | The display of the policy name and policy description with the first letter in lowercase is a deviation from the expected convention and can impact the overall user experience. Urgent attention is required to address this bug and ensure that the system displays the first letter in uppercase for both the policy name and description. | Syed Annas Ahmed